GRAY'S WAREHOUSE MANAGEMENT SYSTEM

Full WMS Implementation Proposal

Phase 2 Complete — From Current 40% to 100%

| Prepared For | Gray's Distribution |
| --- | --- |
| Date | June 2026 |
| Engagement Type | Professional Services — Monthly Rate |
| Version | 1.0 |

1. Executive Summary

Gray's WMS is currently live with Phase 1 — core warehouse, shipping, printing, and Oracle Fusion integration — achieving 75% completion of Phase 1 features and 40% overall. This proposal covers the remaining work to bring the system to full maturity: completing Phase 1 in-progress items and delivering all Phase 2 modules (warehouse structure, receiving, QC, put-away, inventory, picking, dispatch, transport, returns, KPIs, labour management, and mobile devices).

Modules are delivered individually as they complete, so the business gains value continuously rather than waiting for the full six-month project to finish. Two months of on-site presence are included for go-live support, user training, and data migration.

| 6 Months Total Project | 2 Months On-Site Support | $250/Day Daily Rate | $7,500/Mo Monthly Rate |
| --- | --- | --- | --- |

2. Current System Status

The current WMS is a C#/.NET 8.0 Windows Forms application with a WebView2 frontend, communicating with Oracle APEX REST APIs and Oracle Fusion via BIP SOAP.

Phase 1 — Completed Features (19/25)

Trip Management with multi-tab interface

Vehicle and Picker Management

Oracle Fusion Integration (REST + BIP SOAP)

Pick Release and Lot Allocation

Print Management System (Printer config, job queue, monitoring)

Real-time fetching of pending Sales Orders and Store Requests

Assignment of Pickers, Lorries, Priorities, and Loading Bay

Picking and Putaway via Mobile Applications

Ship Confirmation of Orders

Loading Verification via Mobile Applications

Real-time update of Picking/Shipping status into Oracle Fusion

Printing Orders (Shipment Agent with line-count validation)

Vehicle Analytics Dashboard and KPI Cards

Mobile App for Pickers with Barcode/QR scanning

Role-based permissions

Real-time stock levels by warehouse, location, product, lot, expiry

Lot traceability (FEFO), full movement history, cycle counting

Oracle ERP integration for financials & order management

Auto shipping documents (invoices, STV, delivery notes)

Phase 1 — Remaining (6 items — In Progress / Planned)

Advanced Reporting Module (In Progress)

Custom Dashboard Builder (Planned)

Performance Metrics Tracking (Planned)

Customer Delivery Notifications (Planned)

Third-party Carrier Integration (Planned)

3. Phase 2 — Full WMS Requirements (Proposed)

The following modules form the complete Phase 2 scope, aligned directly with the WMS roadmap defined in the application's help page. Each module is self-contained and will be released upon passing user acceptance testing.

| Module | Key Features | Status |
| --- | --- | --- |
| AI & Optimization | AI Readiness framework, Intelligent Picker Assignment using AI, Automated Exception Handling... | Planned |
| Warehouse Structure & Locations | Manage multiple warehouses: Bonded, Duty-Paid, Pharmacy, Cosmetics, RAWS, Triage, Track stock separately for bonded vs. duty-paid status, Support storage types: drive-in racking, selective, double-deep, floor, cold storage... | Planned |
| Receiving Goods | Scan barcodes/QR codes at receipt (pallets, boxes, units), Auto-check received quantities against purchase orders, Handle partial and over-receipts... | Planned |
| Quality Control | Set QC rules by product, supplier, or shipment, Flag items as Non-Conform or On Hold on inspection failure, Digital inspection checklists... | Planned |
| Put-Away | WMS-determined optimal location based on predefined rules, FIFO / FEFO / LIFO / ABC / zone-based storage strategies, Size, weight, hazardous materials & temperature rules... | Planned |
| Inventory Management (Enhancements) | Replenishment triggers: at sight, minimum stock level, picking wave launch, Alerts for picking minimum levels & approaching expiry dates... | Planned |
| Stock Reservation | Reserve stock for specific customers or orders, Show available vs. reserved stock separately, Prevent picking reserved stock for other customers... | Planned |
| Order Management (Enhancements) | Receive orders directly from customers via EDI & e-commerce, Split orders: full pallets vs. less-than-full pallets... | Planned |
| Picking (Enhancements) | Picking methods: single order, batch, zone, wave, cross-docking, Optimize picking routes to minimize travel time, Verify picked items by scanning; handle short picks... | Planned |
| Loading & Dispatch (Enhancements) | Optimize loading sequence; verify quantities by scanning, Assign orders to vehicles & drivers; check vehicle capacity, Delivery by pallets consolidation... | Planned |
| Shipping (Enhancements) | Automatic customer notifications when orders ship, Track proof of delivery (POD) with signatures and photos... | Planned |
| Returns & Reverse Logistics | Handle empty bottle/crate returns with quantity tracking, Track deposit refunds for returnable packaging, Disposition decisions: destroy, rework, braderie, hazardous, ADV... | Planned |
| Performance Tracking (KPIs) | Inventory accuracy, picker efficiency & picking accuracy, Order cycle time, on-time shipment rate, order fulfillment rate, Space utilization, stock aging, near-expiry stock alerts... | Planned |
| Dashboard & Reporting (Enhancements) | Customizable dashboards & role-based views, Alerts & notifications when KPIs breach thresholds, Scheduled automatic report generation & email delivery... | Planned |
| Labour Management | Track individual and team performance, Plan and assign tasks to warehouse staff, Measure active vs. idle time; identify training needs... | Planned |
| Transport Management | Plan & optimize delivery routes automatically, Track transport costs: fuel, maintenance, tyres, tolls, Assign vehicles to routes by capacity & availability... | Planned |
| Mobile Devices & Scanning | Mobile app for warehouse staff (tablets & handheld scanners), Barcode and QR code scanning enhancements, Offline mode with sync when back online... | Planned |
| User Access & Security | Full audit trail — track every system change, Approval workflows for sensitive actions (stock adjustments, write-offs), Two-factor authentication for managers... | Planned |
| Integration with Grays Shops | Product availability & shortage alerts by ABC classification, Automated requisition link to referencing sent to DP... | Planned |
| Implementation & Support | Phased implementation starting with one warehouse, Training for all roles; user manuals & video tutorials (English & French), Ongoing support: critical issues <2hrs, normal <24hrs... | Planned |

4. Project Plan & Timeline

Modules are delivered incrementally — released to production as soon as they pass UAT. The two on-site months (Months 3–4) cover go-live support and user training for all warehouses.

Phase 1 Completion + Warehouse Structure  (Month 1)

Complete Phase 1 remaining items: Advanced Reporting, Dashboard Builder, Customer Notifications

Warehouse Structure & Locations module

AI Readiness framework

Auto-updater and release pipeline

Receiving + QC + Put-Away  (Month 2)

Receiving Goods module (barcode scanning, ASN, GRN printing)

Quality Control module (checklists, Non-Conform flagging)

Put-Away module (FEFO/ABC strategies, mobile-guided)

Inventory Management enhancements (replenishment triggers)

Stock Reservation + Order Management + Picking (ON-SITE begins)  (Month 3)

Stock Reservation module

Order Management enhancements (EDI, pallet splitting)

Picking enhancements (wave/batch picking, route optimization)

ON-SITE: go-live support for Months 1–2 modules, user training

Loading + Shipping + Returns + KPIs (ON-SITE)  (Month 4)

Loading & Dispatch enhancements (manifests, capacity checks)

Shipping enhancements (POD with signatures/photos)

Returns & Reverse Logistics module

Performance Tracking (KPIs) module

ON-SITE: continued training, hypercare support

Dashboard + Labour + Transport + Mobile  (Month 5)

Dashboard & Reporting enhancements (scheduled reports, alerts)

Labour Management module

Transport Management module (route optimization, GPS integration)

Mobile Devices & Scanning enhancements (offline mode)

Security + Integration + Stabilisation  (Month 6)

User Access & Security (audit trail, 2FA, approval workflows)

System Integration enhancements (EDI, e-commerce)

Integration with Grays Shops (shortage alerts, requisitions)

Regression testing across all modules

Documentation, user manuals (English & French), knowledge transfer

Final release with versioned deployment package

High-Level Gantt Summary

| Module / Phase | M1 | M2 | M3 | M4 | M5 | M6 |
| --- | --- | --- | --- | --- | --- | --- |
| Phase 1 Completion + Warehouse | ● |  |  |  |  |  |
| Receiving / QC / Put-Away |  | ● |  |  |  |  |
| Stock Res / OM / Picking |  |  | ● |  |  |  |
| Loading / Shipping / Returns / KPIs |  |  |  | ● |  |  |
| Dashboard / Labour / Transport / Mobile |  |  |  |  | ● |  |
| Security / Integration / Stabilisation |  |  |  |  |  | ● |
| ON-SITE |  |  | ● | ● |  |  |

5. Commercial Terms

Rate Card

| Item | Rate | Notes |
| --- | --- | --- |
| Daily Rate (Remote) | USD 250 / day | Minimum 1 day |
| Monthly Rate (Full Month) | USD 7,500 / month | ~30 working days |
| On-Site Daily Rate | USD 250 / day + T&A actuals | Travel & accommodation billed at actuals |

Investment Summary

| Remote Development (4 months × $7,500) | $30,000 |
| --- | --- |
| On-Site Implementation (2 months × $7,500) | $15,000 |
| Travel & Accommodation (actuals) | TBD |
| Sub-Total (excluding T&A) | $45,000 |
| TOTAL PROJECT BUDGET | $45,000 + T&A |

Payment Terms

Monthly invoicing — invoice raised on 1st of each month.

Payment due within 14 days of invoice date.

On-site travel and accommodation expenses invoiced monthly at actuals with receipts.

Scope changes beyond agreed modules quoted separately.

6. Assumptions & Exclusions

Assumptions

Client provides access to Oracle Fusion ERP (non-production for dev, production for go-live).

Oracle APEX REST services and BIP reports available and configured.

Windows 10/11 workstations available for the desktop WMS application.

Dedicated contact available for requirements clarification within 1 business day.

Existing WMS codebase (javeedin/graysWMSwebviewnew) continues as the base.

Exclusions

Oracle Fusion ERP licencing, configuration, or administration.

Infrastructure, hosting, or cloud services.

Third-party integrations not listed in this proposal.

Data migration from legacy systems (quoted separately if required).

7. Next Steps

Step 1: Review and approve this proposal.

Step 2: Sign engagement letter and confirm start date.

Step 3: Kick-off meeting (remote) — agree module priority order.

Step 4: Schedule on-site dates for Months 3 & 4.

Step 5: Development begins — first module (Phase 1 completion + Warehouse Structure) delivered within 4 weeks of kick-off.

This proposal is valid for 30 days from the date of issue.  |  Prepared by: WMS Development Team  |  June 2026